## Risk Management Responsibilitie
PROJECT MANAGEMENT
Library Management System Project
Risk Management Responsibilities
Person | Responsibilities
System design, and implementing work on web
Team member 1 | Server and website
Team member 2 | Making slides for fyp presentatiom
Team member 3 | Documentation, system design and user interface
Team member 4 | Database connectivity, Query Processing, working on website as well as on server.

## Risk Analysis Summary
PROJECT MANAGEMENT
Library Management System Project
Risk Analysis Summary
Risk Number | Risk Name | Probability Of Occurrence | Impact Description | Responsible Person | Mitigation Action(s)
1 | System power Failure | 7% | Unauthorized user will not be able to access the website. | Team member 1 | Check for the power supplier.
2 | Database Connection Unavailable | 6% | Database transaction will not occur. | Team member 2 | Check for the SQL server running, and connectivity code.
3 | Does not fulfill user requirements | 8% | User knows about this kind of project and expecting different things which are not Beforehand. | Team member 3 | Make it easy to grasp, and alter Accordingly.
4 | System Security | 6% | Systems Security cannot be compromised, different users have different rights. | Team member 3 | Authenticate access of the user, avoiding unauthorized access.
5 | User Dissatisfaction | 5% | Functional Requirements may result in user Dissatisfaction. | Team member 1 | Functional Requirements may result in user Dissatisfaction.
6 | Code Modification | 7% | Last code modifications may cost severely. | Team member 2 | When required modify code and all changes to the relevant fields.